## Slide 1
Smart Check Sheet For Electrical System
Status : Completed to develop EE smart check sheet for Sub #1 on iPad
Schedule : Develop Dashboard to display Sub #1 status / On Plan
Activities | Sep | Oct | Nov
Get Requirement for EE Smart Check Sheet | Done |  | 
Review current check sheet and substation survey | Done |  | 
Design and develop EE Smart check sheet on iPad for Sub#1 | Done |  | 
Design and develop EE Smart check sheet Dashboard for Sub#1 | on going |  | 
User Acceptance Test for Sub#1 |  | Plan | 
Expand to next substation [ Sub #2 – Sub #17 ] |  |  | Plan
Progress Status :
Completed to get requirement ,review current check sheet with team and completed to substation survey
Completed to develop EE smart check sheet for Sub #1 on iPad
Completed to design and create database for EE smart check sheet and deploy to WD server
Design dashboard for display result and make an automatic reports
Next Follow up :
Design dashboard for display result and make an automatic reports
User Acceptance Test for Sub#1
Smart Check Sheet for electrical system on iPad
Current Check Sheet for electrical system